## Risk Register
Ubuntu Innovations (Pty) Ltd - Risk Assessment Matrix
Blue cells are inputs (use the dropdowns for Likelihood/Impact). Scores and ratings recalculate automatically from the Scoring Scale sheet.
ID | Risk | Description | Likelihood | Impact | Risk Score | Rating | Mitigation | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Owner
R1 | Phishing | Staff tricked into revealing credentials or opening malicious links/attachments | High | High | 9 | Critical | Awareness training with simulated phishing; email filtering; MFA on all accounts; simple way to report suspicious email | Medium | Medium | 4 | Medium | IT Support / HR
R2 | Ransomware | Malware encrypts workstations and the NAS, halting operations and demanding payment | Medium | High | 6 | High | Endpoint protection/EDR; daily incremental, weekly full and offsite cloud backups (incl. an offline/immutable copy); patching; least-privilege folder access | Low | High | 3 | Medium | IT Support
R3 | Hardware failure | Failure of a PC, NAS disk, switch, router or access point | Medium | Medium | 4 | Medium | RAID on NAS; spare switch/power supply; warranty and support contracts; standard PC image for fast replacement | Low | Medium | 2 | Low | IT Support
R4 | Power outage / load shedding | Loss of mains power damaging equipment or interrupting work | Medium | High | 6 | High | 2 x 1500VA UPS for router, switch and NAS; safe-shutdown configuration; consider inverter/generator backup | Low | Medium | 2 | Low | IT Support / Management
R5 | Weak or compromised passwords | Guessable, reused or stolen passwords give attackers account access | Medium | High | 6 | High | Password complexity policy; MFA; password manager; account lockout; disable accounts promptly on exit | Low | Medium | 2 | Low | IT Support
R6 | Lost or stolen laptop | Loss of one of the 5 management laptops exposes company data | Medium | High | 6 | High | Full-disk encryption; screen lock; remote wipe; asset register; no local-only data storage | Medium | Low | 2 | Low | IT Support / Management
R7 | Unpatched or outdated software | Known vulnerabilities left open on operating systems and applications | High | Medium | 6 | High | Scheduled patch management; automatic OS and antivirus updates; monthly patch review | Low | Medium | 2 | Low | IT Support
R8 | Internet / ISP outage | Loss of connectivity affecting email, cloud tools and offsite backups | Medium | Medium | 4 | Medium | Fibre SLA with the ISP; 4G/5G failover on the router; offline-capable cloud tools | Low | Medium | 2 | Low | IT Support
R9 | Accidental deletion / human error | Files deleted or overwritten by mistake | Medium | Medium | 4 | Medium | NAS snapshots; file version history; restricted write permissions; tested restore procedure | Low | Low | 1 | Low | IT Support
R10 | Unauthorised access / insider threat | Staff accessing data outside their department or misusing privileges | Low | High | 3 | Medium | Department security groups (least privilege); audit logging on Finance and HR folders; onboarding/offboarding checklist | Low | Medium | 2 | Low | IT Support / HR
R11 | Personal data breach (POPIA) | Exposure of HR and Finance personal information, with legal and reputational impact | Low | High | 3 | Medium | Encryption at rest and in transit; restricted HR/Finance folders; Incident Response Plan with breach-notification steps | Low | Medium | 2 | Low | Management / IT Support
R12 | Physical theft / unauthorised office access | Equipment stolen or comms room accessed by unauthorised people | Low | Medium | 2 | Low | Lockable comms cabinet for router, switch and NAS; entrance access control; visitor log | Low | Low | 1 | Low | Management

## Scoring Scale
Scoring Scale
Risk score = Likelihood x Impact. Blue values are inputs; the Risk Register looks them up from here.
Level | Value
Low | 1
Medium | 2
High | 3
Rating bands (minimum score)
Rating | Min score | Response
Low | 1 | Accept and monitor
Medium | 3 | Mitigate within normal operations
High | 6 | Mitigate as a priority
Critical | 9 | Immediate, top-priority controls
Likelihood and impact descriptions
Assumption: ratings for R1-R4 follow the capstone brief; R5-R12 are additional risks identified for a 25-user Cape Town office.

## Heat Map
Risk Heat Maps
Risk IDs are pulled from the Risk Register automatically. Cell colour shows the rating of that Likelihood x Impact combination.
Inherent risk (before mitigation)
Likelihood \ Impact | Low | Medium | High
High |  | R7 | R1
Medium |  | R3, R8, R9 | R2, R4, R5, R6
Low |  | R12 | R10, R11
Residual risk (after planned mitigation)
Likelihood \ Impact | Low | Medium | High
High
Medium | R6 | R1
Low | R9, R12 | R3, R4, R5, R7, R8, R10, R11 | R2
Summary: number of risks by rating
Rating | Inherent | Residual
Critical | 1 | 0
High | 5 | 0
Medium | 5 | 2
Low | 1 | 10
Total | 12 | 12